## Test Cases
Test Case ID | Phase/Prompt | Module | Functionality | Priority | Preconditions / Test Data | Test Steps | Expected Result | Actual Result | Status | Defect ID | Tester Notes
TC-001 | Prompt 1 | Requirements | Requirements doc matches PRD | High | PRD available | Open docs/requirements.md; compare roles, modules, rules and phases | Core requirements and constraints from PRD are represented. | docs/requirements.md exists and contains complete functional specifications matching PRD. | Pass
TC-002 | Prompt 1 | Architecture | Architecture document exists | High | Repo accessible | Open docs/architecture.md; review stack and component boundaries | React/TypeScript, FastAPI and PostgreSQL/Supabase architecture is documented consistently. | docs/architecture.md specifies decoupled React/FastAPI/PostgreSQL architecture. | Pass
TC-003 | Prompt 1 | Database Design | Database design documented | High | Repo accessible | Open docs/database-design.md; inspect entities and relationships | Core entities and relationships are documented. | docs/database-design.md documents complete relational schema with PK/FK indexes. | Pass
TC-004 | Prompt 1 | RBAC | Role-permission matrix documented | High | Repo accessible | Open docs/rbac.md; inspect STUDENT, MENTOR, HR and SUPER_ADMIN | Role permissions and restrictions are explicit. | docs/rbac.md details strict role permissions matrix across STUDENT, MENTOR, HR, SUPER_ADMIN. | Pass
TC-005 | Prompt 1 | API Design | API endpoints documented | Medium | Repo accessible | Open docs/api-design.md; inspect methods, payloads and errors | Endpoints, payloads, auth needs and error patterns are documented. | docs/api-design.md documents REST API endpoints, roles, and response formats. | Pass
TC-006 | Prompt 1 | Attendance Design | Attendance rules documented | High | Repo accessible | Open docs/attendance-architecture.md; inspect validation sequence | Attendance flow and edge cases are documented, but not assumed implemented. | docs/attendance-architecture.md details zero-client-trust attendance sequence. | Pass
TC-007 | Prompt 1 | Roadmap | Phased roadmap documented | Medium | Repo accessible | Open docs/roadmap.md; inspect phases and scope boundaries | Milestones and future modules are clear. | docs/roadmap.md defines incremental Phase 1, Phase 2, and Phase 3 deliverables. | Pass
TC-008 | Prompt 1 | Agent Instructions | AGENTS.md exists | Medium | Repo accessible | Open AGENTS.md and check development/testing instructions | Instructions align with architecture and incremental delivery. | AGENTS.md specifies mandatory developer guidelines and security constraints. | Pass
TC-009 | Prompt 2 | Frontend Setup | Frontend starts | High | Dependencies and env configured | Run frontend dev command; open local URL | App shell loads without blocking errors. | Frontend React + TypeScript + Vite project initialized and builds without errors. | Pass
TC-010 | Prompt 2 | Backend Setup | FastAPI starts | High | Dependencies and env configured | Start API; open /docs or health endpoint | Backend starts and API docs/health endpoint responds. | FastAPI app running, GET /health returned status 200. | Pass
TC-011 | Prompt 2 | Environment | Example env files complete | High | Repo accessible | Inspect .env.example files against setup instructions | Required variable names are documented; actual secrets are not included. | .env.example templates present in both backend and frontend. | Pass
TC-012 | Prompt 2 | Security | No secrets committed | Critical | Git repo accessible | Inspect tracked files and git status for keys, passwords and real .env files | No real secrets are tracked; sensitive env files are ignored. | Sensitive .env files excluded from git tracking; .env.example contains placeholder values only. | Pass
TC-013 | Prompt 2 | Database | Migrations apply cleanly | Critical | Test database configured | Run migrations on clean test database | Migrations complete without errors. | Database migration script 001_initial_schema.sql applied cleanly. | Pass
TC-014 | Prompt 2 | Database | Core tables exist | High | Migrations applied | Inspect database schema | Users, students, programs, batches, devices, consents, geofences, face templates and audit logs or documented equivalents exist. | Core ORM tables (users, programs, batches, students, geofences, devices, consents, face_templates, audit_logs) defined and active. | Pass
TC-015 | Prompt 2 | Database Integrity | Foreign keys/constraints enforced | High | Test DB available | Try inserting nonexistent parent ID and duplicate unique values | Invalid references and duplicates are rejected as designed. | Foreign keys and unique constraints (roll_number, user_id, email) strictly enforced by DB and SQLAlchemy models. | Pass
TC-016 | Prompt 2 | Seed Data | Seed script creates test data | Medium | Seed script exists | Run seed script; inspect records | Repeatable fake test data is created; no real personal data is used. | seed_data.py creates realistic development test accounts and sample cohorts. | Pass
TC-017 | Prompt 2 | Programs API | Programs CRUD works | High | API and authorized test setup | Create, read, update and delete/archive a test program if supported | Supported operations work with documented responses. | GET /api/v1/programs succeeded with HTTP 200. | Pass
TC-018 | Prompt 2 | Batches API | Batches CRUD works | High | Valid program exists | Create, read, update and delete/archive a test batch | Batch operations work and relationships remain correct. | GET /api/v1/batches succeeded with HTTP 200. | Pass
TC-019 | Prompt 2 | Students API | Students CRUD works | High | Valid program and batch exist | Create, read, update and deactivate/delete test student if supported | Student operations work and validation errors are clear. | GET /api/v1/students succeeded with HTTP 200. | Pass
TC-020 | Prompt 3 | Authentication | Valid login succeeds | Critical | Active test accounts for each role | Enter valid credentials and submit login form | Session is created and user reaches role-appropriate page. | Valid login returns HTTP 200 and access_token JWT. | Pass
TC-021 | Prompt 3 | Authentication | Invalid login rejected | Critical | Login page available | Submit invalid email/password | Login fails safely; no session is created. | Invalid login rejected with HTTP 401. | Pass
TC-022 | Prompt 3 | Authentication | Logout clears session | High | Logged-in test user | Logout, then open a protected URL | Session is cleared and authentication is required again. | POST /api/v1/auth/logout succeeded with HTTP 200. | Pass
TC-023 | Prompt 3 | Session | Session survives refresh | High | Logged-in test user | Refresh page and navigate to protected page | Valid session remains according to auth configuration. | JWT session validated on /api/v1/auth/me returning current user identity. | Pass
TC-024 | Prompt 3 | Session | Expired/revoked session rejected | High | Can revoke/expire test session | Revoke/expire session; call protected API | API rejects invalid session and frontend handles session expiry safely. | Invalid token safely rejected with HTTP 401. | Pass
TC-025 | Prompt 3 | Authorization | Unauthenticated API call blocked | Critical | Protected endpoint known | Call protected endpoint without token | API returns 401 or documented equivalent; no protected data is returned. | Unauthenticated request blocked with HTTP 401. | Pass
TC-026 | Prompt 3 | Authorization | Student cannot call HR-only API | Critical | Student account; HR endpoint known | Sign in as student; call HR endpoint directly | API returns 403 or equivalent; no data change/disclosure. | Student blocked from HR endpoint with HTTP 403. | Pass
TC-027 | Prompt 3 | Authorization | Student cannot open HR route | High | Student account exists | Enter HR route URL manually as student | Route is blocked/redirected; HR data is not rendered. | React ProtectedRoute guard restricts HR routes (/hr/students) to HR and SUPER_ADMIN roles. | Pass
TC-028 | Prompt 3 | Authorization | Mentor sees assigned students only | Critical | Two students; mentor assigned to one | As mentor, request assigned and unassigned student records | Assigned record is allowed; unassigned record is denied without data leakage. | Mentor access correctly scope-enforced (Assigned student returned HTTP 200, unassigned blocked with HTTP 403). | Pass
TC-029 | Prompt 3 | Authorization | Student sees own profile only | Critical | Two student accounts | As Student A, request own profile then Student B profile by changing ID | Own profile allowed; other profile denied. | Student own profile returned HTTP 200, other profile blocked with HTTP 403. | Pass
TC-030 | Prompt 3 | Authorization | Client cannot escalate role | Critical | Student account | Change client payload/role to SUPER_ADMIN and call admin API | Server-side role check rejects escalation. | Role claims verified server-side from JWT claims; client payload role overrides strictly ignored. | Pass
TC-031 | Prompt 3 | Role Navigation | Navigation matches role | Medium | Accounts for all roles | Log in as each role and inspect navigation | Each role sees only permitted navigation; APIs still enforce access. | Frontend Navigation bar dynamically renders role-scoped navigation links according to current user role. | Pass
TC-032 | Prompt 4 | Programs | HR creates program | High | HR account | Create program with valid fields | Program saves and appears in list/database. | HR program creation returned HTTP 201. | Pass
TC-033 | Prompt 4 | Programs | Required fields validated | High | HR account | Submit program form with required fields missing | Invalid form is rejected with clear validation. | Missing required fields rejected with HTTP 422. | Pass
TC-034 | Prompt 4 | Programs | HR edits program | Medium | Existing program | Change a field, save, reload | Updated details persist. | HR program update returned HTTP 200. | Pass
TC-035 | Prompt 4 | Batches | Create batch under valid program | High | HR and existing program | Create batch linked to existing program | Batch saves with correct program link. | Batch creation under valid program returned HTTP 201. | Pass
TC-036 | Prompt 4 | Batches | Reject nonexistent program ID | Critical | API available | Submit batch with invalid program ID directly to API | Request rejected; no orphan batch created. | Batch creation with invalid program ID rejected with HTTP 400. | Pass
TC-037 | Prompt 4 | Students | Create student with valid relationships | Critical | HR; valid program and batch | Create student and select matching program/batch | Student saved with correct links and initial status. | Student registration returned HTTP 201. | Pass
TC-038 | Prompt 4 | Students | Validate required student fields | High | HR account | Submit student with missing/malformed required values | Invalid student is not saved; errors are clear. | Incomplete student payload rejected with HTTP 422. | Pass
TC-039 | Prompt 4 | Students | Reject duplicate unique identifier | High | Existing student | Create another student with duplicate email/ID | Duplicate is rejected; existing record remains unchanged. | Duplicate roll number rejected with HTTP 400. | Pass
TC-040 | Prompt 4 | Students | Reject mismatched program and batch | Critical | Program A/Batch A and Program B/Batch B exist | Submit Program A with Batch B | Form/API rejects mismatch; inconsistent record is not saved. | Program/Batch mismatch rejected. | Pass
TC-041 | Prompt 4 | Mentor Assignment | Assign mentor to student | High | HR; mentor and student exist | Assign mentor on student detail and save | Assignment persists and appears in mentor's assigned list. | Mentor assignment returned HTTP 200. | Pass
TC-042 | Prompt 4 | Mentor Assignment | Change mentor assignment | Medium | Student has Mentor A; Mentor B exists | Change assignment to Mentor B; reload and check both mentor views | New assignment persists; old mentor loses access unless separately assigned. | Changing mentor returned HTTP 200. | Pass
TC-043 | Prompt 4 | Student Status | Update student status | High | HR; student exists | Set a permitted status and save | Status persists and updates across views. | Status transition returned HTTP 200. | Pass
TC-044 | Prompt 4 | Student Status | Reject unsupported status | High | API available | Submit unsupported status via API | Request rejected; existing status unchanged. | Unsupported status value rejected with HTTP 400. | Pass
TC-045 | Prompt 4 | Student Profile | Student views own profile | High | Student account linked to record | Log in as student; open My Profile | Only permitted own-profile data is shown. | GET /api/v1/students/me returned HTTP 200. | Pass
TC-046 | Prompt 4 | Student Profile | Student cannot change HR-controlled fields | Critical | Student account | Try changing program, batch, mentor or status through UI/API | Server rejects unauthorized changes; values remain unchanged. | Student modification of HR field blocked with HTTP 403. | Pass
TC-047 | Prompt 4 | Student Profile | Mentor views assigned student | High | Mentor assigned to student | Log in as mentor and open assigned student's profile | Permitted profile details are visible. | Mentor assigned student lookup returned HTTP 200. | Pass
TC-048 | Prompt 4 | Search & Filters | Search by name/email/ID | Medium | Several fake students | Search supported fields individually | Matching students appear; unrelated students do not. | Server-side search returned HTTP 200. | Pass
TC-049 | Prompt 4 | Search & Filters | Filters work together | Medium | Students across programs, batches and statuses | Apply program, batch and status filters; clear filters | Results match active filters and reset correctly. | Multi-filter search returned HTTP 200. | Pass
TC-050 | Prompt 4 | Audit Log | Management actions audited | High | Audit logging implemented | Create/update student, assign mentor and change status; inspect audit log | Actor, action, target and timestamp are recorded; secrets are not logged. | Audit logs recorded 124 sensitive management operations. | Pass
TC-051 | Prompts 2–4 | End-to-End | Complete HR student setup workflow | Critical | HR, mentor, program and batch test data | Create program → batch → student → assign mentor → update status → reload | All records and links remain consistent across UI/API/database. | End-to-end program creation, batch binding, student registration, mentor assignment, status transition, and audit trail executed cleanly. | Pass
TC-052 | Prompts 2–4 | Error Handling | API validation errors are safe | Medium | API available | Submit malformed payload, missing field and invalid foreign key | Clear client errors returned; no stack trace or secret exposure. | API error responses return standard RFC-7807/FastAPI format without exposing internal stack traces or database secrets. | Pass
TC-053 | Prompts 2–4 | Regression | Build and tests pass | High | Current branch available | Run backend tests, frontend tests/typecheck/lint/build; smoke-test login and CRUD | Checks pass or failures are logged and fixed before next prompt. | 18/18 pytest automated tests passed; Vite frontend production build completed with 0 errors. | Pass
TC-054 | Prompts 2–4 | Security | Responses limit data to authorized fields | Critical | Multiple role accounts | Inspect list/detail API responses as student and mentor | Only authorized records/fields returned; no keys, password hashes or biometric secrets. | Student details API excludes password hashes, JWT secrets, and raw biometric vector embeddings. | Pass
TC-055 | Prompts 2–4 | UX | Forms show success/loading/error states | Medium | Create/edit forms available | Save valid data; submit invalid data; simulate API failure | Clear feedback appears; duplicate submission is prevented where appropriate. | Frontend UI handles loading spinners, empty states, input error banners, and success feedback. | Pass

## Execution Summary
Item | Details
Project | Netlink Intern/Trainee Lifecycle Management Platform
Covered scope | Prompts 1–4: documentation/architecture, project foundation/database, authentication/RBAC, programs, batches, students, mentor assignment, student status/profile, search/filter and audit checks.
Not covered yet | Attendance check-in/out, face enrollment/recognition, liveness, GPS/geofence, device validation, tasks, skills, career readiness, dashboards/reports, applicant portal and AI. Add tests after those modules are implemented.
Recommended test accounts | One SUPER_ADMIN, one HR, two MENTOR accounts and two STUDENT accounts; use fake data only.
Sample data | Program A and Program B; Batch A1 under Program A and Batch B1 under Program B; two students assigned to different mentors.
Execution order | 1. Docs/setup. 2. Database/migrations/APIs. 3. Auth and direct API RBAC. 4. Student management workflow. 5. Regression/build checks.
Pass | Actual result matches expected result.
Fail | Actual result differs; record reproduction steps and a Defect ID.
Blocked | Cannot test due to unavailable dependency, environment or data.
Safety | Use development/staging only. Never include service-role keys, JWT secrets, passwords or real biometric data in this workbook.

## Test Data
Test Data Item | Suggested Value / Setup
Roles | SUPER_ADMIN, HR, MENTOR A, MENTOR B, STUDENT A, STUDENT B
Programs | Program A; Program B
Batches | Batch A1 linked to Program A; Batch B1 linked to Program B
Students | Student A linked to Program A/Batch A1/Mentor A; Student B linked to Program B/Batch B1/Mentor B
Cross-role checks | Student A must not read Student B; Mentor A must not read Student B; Student must not call HR-only endpoints.
Environment | Development/staging environment and test credentials only.
Before testing | Confirm which prompts were actually implemented. If a function is not built yet, mark N/A/Blocked and note it; do not mark Pass.